## Slide 1: Nevada SPCSA
Grants Administration and Funding Innovation Presentation, December 2018
Developed by the Strategic Progress Team Principal Investigator, Dr. Justin S Gardner of anchor partner Innovative Research and Analysis LLC

## Slide 2: Project Team Objectives
Fully investigate and analyze required resources and responsibilities for the Nevada SPCSA to operate as an LEA that provides federal/state grant management services for 29 sponsored charter schools and for 21+ federal and state grant programs.
  Specifically provide “best-practice” recommendations related to staffing and business process efficiencies based on: (1) management of 8 current funding streams, and (2) for expanded operations that could include 13+ additional funding streams.
Recommend “best-practice” service delivery procedures related to grant funds management for the Nevada SPCSA and sponsored charter schools in transitioning sponsored charter schools to becoming their own LEAs.
  Investigate and recommend the minimum required capabilities of charter school operators functioning as their own LEA for managing federal and state grant funds.
  Develop and recommend procedures for evaluating the capabilities of an independent charter school operator to manage federal/state grant funds as their own LEA.
  Explore and recommend training and/or support that a charter school operator would need for managing federal/state grant funds while transitioning to their own LEA.

## Slide 3: Current Status of Project Activities
Project Deliverable or Activity | Sub-categorization Deliverable or Activity | Status as of 5 December 2018
Conduct a GAP analysis of Nevada SPCSA management of federal and state grant programs to understand what is currently happening and what ideally would happen for the Nevada SPCSA if expected restructuring of service delivery occurs. |  | Research and Report Development: In-Progress Analysis: Not sufficient data and information to conduct formal analysis
 | Focus on federal/state funding pass throughs and grant management-related Local Educational Agency operation from a liability management, compliance, and school empowerment perspective. | Data Request to Nevada Department of Education (NDE): Data Request Submitted – Currently, outstanding; Survey of Charter Schools: Completed (n=18) Collaboration: On-Going
 | This will be heavily weighted/anchored on review of comparable LEA operations in Nevada and/or in other comparable states and will consider LEA requirements, regulations, best practices, funding innovation, and engagement with schools, to include: | Collaborative Research: In-Progress Analysis and Recommendation Development: Not sufficient data and information to conduct formal analysis
 | 1. Investigation of minimum required capabilities of charter schools to function as their own LEA to manage federal and state grant funds. | Currently and Publicly Available Grant Funding Investigation: Completed NDE Administered Grants: Data Request Submitted – In-Progress
 | 2. Will lead to the development of recommendations for SPCSA in determining charter schools for LEA responsibilities. | Recommendation Development: Not sufficient data and information to conduct formal analysis

## Slide 4: Current Status of Project Activities
Project Deliverable or Activity | Sub-categorization Deliverable or Activity | Status as of 5 December 2018
Conduct a process assessment of how funds flow between the Nevada Department of Education, the Nevada SPCSA, and sponsored schools to help make recommendations to streamline and improve efficiencies and guide development of recommendations for Study deliverables. Assess grant data, lay out reporting/monitoring plans and processes, and make recommendations for accountability. |  | Currently and Publicly Available Grant Funding Investigation: Completed NDE Administered Grants: Data Request Submitted – In-Progress Survey of Charter Schools: Completed (n=18) Recommendation Development: Not sufficient data and information to conduct formal analysis
 | Will lead to the development of recommended “best-practice” service delivery procedures related to grant funds management for the Nevada SPCSA and sponsored charter schools in transitioning sponsored charter schools to becoming their own LEAs. | Best Practice Research: In-Progress Collaboration: On-Going Recommendation Development: Not sufficient data and information to conduct formal analysis
 | Additionally, this will include development of recommended procedures for evaluating the capabilities of an independent charter school operator to manage federal/state grant funds as their own LEA in concert with A1-a.2 above. | Recommendation Development: Not sufficient data and information to conduct formal analysis

## Slide 5: Current Status of Project Activities
Project Deliverable or Activity | Sub-categorization Deliverable or Activity | Status as of 5 December 2018
Research allowable and unallowable expenditures for current and projected funding streams and provide support in creating guidance document library for SPCSA staff. Liability management, integration/coordination of funds, and funding innovation will be emphasized. |  | Currently and Publicly Available Grant Funding Investigation: Completed NDE Administered Grants: Data Request Submitted – In-Progress
Investigate and analyze additional areas for consideration in the GAP analysis as needed. |  | Recommendation Development: Not sufficient data and information to conduct formal analysis
 | This will include the exploration and recommendation of training and/or support that a charter school operator would need for managing federal/state grant funds while transitioning to their own. | Currently and Publicly Available Grant Funding Investigation: Completed NDE Administered Grants: Data Request Submitted – In-Progress Survey of Charter Schools: Completed (n=18)
Coordinate with collaborators for research/discovery activities and regularly communicate findings. Collaborators include Adam Hawf’s Development Team (an additional contractor group working on other aspects of the Study), and the Nevada SPCSA staff. |  | Collaboration: On-Going SPCSA Meetings: Formal meetings weekly, Ad hoc meetings as needed
Final Reporting (Comprehensive GAPS Analysis and Assessment Report) and Recommendation Brief (Staffing, Process, Program, Training, Road Map) Development |  | Research: In-Progress Final Report Development: In-Progress Recommendation Briefs: Not sufficient data and information to develop; however, draft format In-Progress

## Slide 6: Proposed Policy Analysis Assessment Model
Alternative | LEA Options
Alternative 1: No Action Alternative | Current SPCSA Operation
Alternative 2: Current Plus Alternative | SPCSA as Authorizer Only*
Alternative 3: Fully Operational LEA | SPCSA as District-LEA*
Alternative 3a: Mixed-Current Operation Model | SPCSA as District LEA for specific funds
Alternative 4: Intermediary Operation | SPCSA as Intermediate Unit of the State (ESA)*
Alternative 4a: Mixed-Fully Operational Model | SPCSA as District LEA and ESA (capacity-basis)
*These LEA Structure Options were developed and provided by separate consulting group to SPCSA through collaborative project approach as summarized in this Executive Summary Report. | 
The current statutory parameters of the Nevada SPCSA provide operational capacity to operate as an LEA. Future legislative activities could be utilized to streamline and expound upon currently allowed statutory operations. That said, as previously discussed, the SPCSA will be transitioning towards a broader application of operational parameters approaching a more fully functional LEA.
The recommended model(s) presented on the subsequent slide offer a strategic and phased implementation these operational transitions.

## Slide 7: Anticipated Recommendation from Policy Analysis Assessment Model
Implementation Plan | Alternative | LEA Options | Explanation of Option
Phase 1, 2-3-year implementation plan to migrate SPCSA to fully operational LEA by the 2021-22 school year. | Alternative 3a: Mixed-Current Operation Model | SPCSA as District LEA for specific funds | The SPCSA serves as an LEA with full responsibilities and capacities but is designed to support staged or phased implementation. This implementation plan would include a 2-3-year implementation phase with the goal of the SPCSA becoming a fully functioning LEA for all available grant funds. While SPCSA would inherit all operational capacities of an LEA beginning in Year 1 (2019-20), there would be substantial LEA-based infrastructure developed during the first operational year. In Year 2 (2020-21) implementation year infrastructure would be further supported and expanded to include development of standardization guides; evaluation criteria, schedule and plans; compliance and QA/QC expectations; program specific operations, funding, and staffing; and standardized training pursuant to grants administration and management. Finally, in Year 3 (2021-22) the SPCSA would be fully operational with all staffing and support needs identified and solutions either implemented or developed. By the end of Year 3, grant funding innovation analysis should be possible to identify expanded funding opportunities and a Standard Operating Procedure for individual or jointly established school-level LEAs.
Phase 2, 1-2-year implementation plan following successful implementation of SPCSA as a fully operational LEA | Alternative 4a: Mixed-Fully Operational Model | SPCSA as District LEA and ESA (capacity-basis) | The SPCSA serves as an LEA with full responsibilities and capacities as noted above but provides opportunities for charter schools or jointly established charter school LEAs. While some responsibilities pursuant to grants administration would be passed directly to individual or jointly established LEAs, SPCSA would retain financial oversight to include Quality Assurance (QA) and retain capacity to hold back funding to individual or jointly established LEAs pursuant to funding requirements and regulations.

## Slide 8: Staffing Assessment Pursuant to LEA Operation STandards
E275: Data Integrity Resources
3 new positions all under School Support Deputy Director:
  Education & Information Officer (Grade 35)
  Education Programs Professional* (Grade 39)
  Administrative Assistant IV (Grade 29)
Educate and inform schools of: accountability expectations, reporting requirements, and compliance requirements.
Act as portfolio-wide testing coordinator for SPCSA-sponsored schools.
Perform assessment data validation and report compilation.
E276: Expanded LEA Resources
5 new positions: 2 reporting to School Support Deputy Director & 3 reporting to Finance & Operations Admin Services Officer III:
  Educational Programs Professional (Grade 39)
  Educational Programs Professional (Grade 39)
  Accounting Assistant IV* (Grade 29)
  Accounting Assistant III (Grade 27)
  Grants & Projects Analyst (Grade 35)
Manage 13 or more additional state or federal grant funding streams/programs.
Provide school support for additional responsibility required as a LEA for SPCSA-sponsored schools.
Minimum of additional $12 million per year in revenue authority.
E277: New Executive Assistant Position
1 new position reporting directly to the Executive Director:
  Executive Assistance (UC)
Provide administrative support to Board, Executive Director, and Staff Attorney and act as the agency public records official.
Draft agendas, prepare minutes, and coordinate documentation for board meetings.
Track board meeting action items for completion, file court documents, and respond to Open Meeting Law issues.
Fully supported, there will be 9 new SPCSA staff that will support the management of 13 additional grant programs with 75 active grants, which could increase with expanded school support, eligibility assessments, and funding innovation.
Currently, 17 SPCSA staff that manage 9 grant programs with 89 active grants across SPCSA-sponsored schools.
In summary, 9 new positions to more than double grant programs and nearly double active grants. Unaddressed areas of need: Grant Program Training (staff and school); Compliance and Quality Assurance/Quality Control;
Grant Evaluation; Strategic Implementation Process/Plan.

## Slide 9: Overview of ANTICIPATED RECOMMENDED MODEL, STAFFING NEEDS, and EXISTING NEEDS
Based on available information the Phased Implementation of the SPCSA as a full LEA over a 2-3-year time period has been identified as the likely recommended model with full operational capacity inherited by SPCSA beginning in 2019-20 (Year 1).
  Following the 2-3-year implementation, we recommend a holistic assessment of grouped or individualized LEA formations that should not account for more than two-thirds of sponsored schools.
Fundamentally, there are not sufficient staff at the SPCSA to operate as a full LEA and the currently requested 9-additional positions will not adequately address staffing needs.
  An additional 5-7 full-time positions are estimated as mission critical to SPCSA LEA operations with additional third-party contracted support for specialized operations related to currently unmet needs:
    Grant Program Training (staff and school);
    Compliance and Quality Assurance/Quality Control;
    Grant Evaluation;
    Strategic Implementation Process/Plan
  An additional 2-6 full-time positions are estimated as mission critical to SPCSA LEA operations with respect to special education services and compliance.
Strategic staffing assessments and decision-making in addition to funding innovation are considered major priorities to expanding SPCSA staff.

## Slide 10: Pathway towards Sustainable SPCSA LEA Operations
Phased Implementation of SPCSA as a fully operational LEA (as previously presented)
  Strategic Implementation Plan development
  Strategic Staffing Assessment
  Annual Evaluation and Benchmarks
Data system:
  Assessment and integration of all data systems,
  Improved data integrity,
  Increased data sharing, and
  Expanded reporting capacities at SPCSA and individual charter schools
Increased staffing:
  Approval of 9 currently requested positions;
  Plans to hire 5-7 additional staff members during implementation (training; compliance and QA/QC; evaluation);
  Plans to hire 2-6 additional staff members during implementation for special education services and compliance; and
  Third-party contracting agreements for specialized support.
Standardized Grant Training for SPCSA staff:
  Training design and administration should provide scalability to school-level staff training
  Administration through online Learning Management System (LMS)
Compliance, QA/QC, and Grant Evaluation (Policies & Procedures and Implementation Strategy):
  Standardized training for staff and schools and/or
  Administration by third-party contractor

## Slide 11: Project Team Contacts & Questions
Project Team Contacts:
Ms. Cyndy Ortiz Gustafson, MA: Project Manager
Founder & CEO, Strategic Progress, LLC
cyndy@strategicprogress.com
Dr. Justin S Gardner: Principal Investigator and Project Team Lead
Founder & CEO, Innovative Research and Analysis LLC (Anchor Partner: Strategic Progress, LLC)
justin.gardner@innov8reanalysis.com
Questions?