## Table 1
GALS Las Vegas Action Plan P= Primary; S= Secondary; C= Consultant Task/ Planning Area/ Timeline | ED | HOS | GALS | Staff | BOD | Volunteers | Prior | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Completed
Student Recruitment & Admissions (Marketing)
Board Strategic Planning
Create Enrollment Plan and Policy | P | S | [19 empty] | X
Execute Enrollment plan | P | S |  | S | S
Check-ins on Enrollment Process | S |  |  |  | P
Informational Flyer
Prepare marekting materials (English and Spanish) | S |  | P |  | P | [16 empty] | X
1500 flyers ready for distribution | P | [20 empty] | X
Develop marketing message (value propostiion) | P |  |  | S | S | S | [15 empty] | x
Preliminary website | S |  | P | [18 empty] | x
School website | P |  | S | [18 empty] | x
Create & Order 5,000 postcards for mailer and distribution | P | [20 empty] | x
Conduct door to door canvasing | P |  |  |  | S | S | [15 empty] | x
Distibute materials in public spaces | P
Engage community organizatinos (BGC, Rec Center) | P
Initiate broader recruiting and marketing campaign via advertisements, etc.- (additional marketing to community) | P | C | S | S | S
Enrollment Form
Design student enrollment form | P | [20 empty] | X
Translate form into Spanish | P | [20 empty] | X
Make enrollment form available | P | [20 empty] | X
Post enrollment form on website | P | [20 empty] | x
Information Sessions
Secure locations for information sessions | P | [20 empty] | X
Create sign up sheets for information sessions. | P
Host information sessions | P | S
Publicity Campaign
Research all community and LV based publications, radio stations, tv - contact | P | [20 empty] | X
Write English press release | P | [20 empty] | X
Translate release into Spanish | P | [20 empty] | X
Distributte press relaase | P | [20 empty] | X
GALS Las Vegas Action Plan P= Primary; S= Secondary; C= Consultant Task/ Planning Area/ Timeline | ED | HOS | GALS | Staff | BOD | Volunteers | Prior | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Completed
Admissions Lottery and Enrollment
Develop Enrollment policy and forms | S | P |  | S | C | [16 empty] | X
Collect forms | P | S |  | S
Administer lottery if needed | P | S |  | S | [17 empty] | X
Confirm acceptances | P | S |  | S
Request student records | P | S |  | S
Receive student records | P | S |  | S
Facilities
Develop list of Facility wants, needs, renovatoins and general budgeting | P |  |  |  | C | [16 empty] | X
Determine Brokering Agency | P |  |  |  | C | [16 empty] | x
Develop list of top three sites | P | C | C | C | C | C | [15 empty] | X
Get real estate expert to view and evaluate sites | P |  |  |  | C | [16 empty] | X
Negotiate lease | P |  |  |  | C | [16 empty] | x
Sign lease | P |  |  |  | C
Secure financing | P |  |  |  | C | [16 empty] | X
Perform renovations if necessary | P |  |  |  | C
Pass final inspection and receive occupancy certificate | P |  |  |  | C
Governance
Board Structure
Recruit and nominate new Board members | P |  |  |  | P | [16 empty] | X
Train board Members | P | [20 empty] | X
Implement Open meeting law | P | S | C |  | C | [16 empty] | X
Develop and ratify by-laws (Set by May 12) | C | C | C |  | P | [16 empty] | X
Develop Conflict of Interest Policy (Set by May 12) | C | C | C |  | P | [16 empty] | X
Develop Ethics policy (Set by May 12) | C | C | C |  | P | [16 empty] | X
Develop Governance Policy (board expectations - TFG Expectations) (Set by May 12) | C | C |  |  | P | [16 empty] | X
Develop governance strategy
Arrange Board liability | P | S | [19 empty] | x
Offboard and onboard upon charter approval | C |  |  |  | P
Charter | S |  |  |  | P | [16 empty] | x
CMO Agreement | S |  |  |  | P | [16 empty] | x
Develop Master Board Calendar and TFG Calendars (by April 15) | P | S | [19 empty] | x
Board Meetings
GALS Las Vegas Action Plan P= Primary; S= Secondary; C= Consultant Task/ Planning Area/ Timeline | ED | HOS | GALS | Staff | BOD | Volunteers | Prior | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Completed
Pick set day and time to consistently hold meetings. Print schedule. Follow postings for Open Meeting Law. | C | C |  |  | P | [16 empty] | x
Develop agenda format | P | S | [19 empty] | x
Develop consistent format for board meeting packets (that go out 2 wks. prior to board meetings). | P | S | [19 empty] | x
Start making meetings more "formal." Get in practice prior to having members from the public in attendance. | C | C |  |  | P | [16 empty] | x
Have observers attend meetings to give feedback about process, facilitation, etc. | C |  |  |  | P | [16 empty] | x
Start creating formal meeting minutes. Minutes are legally binding - get outside party to review to make sure we are doing it properly. | P | S | [19 empty] | x
Create mechanisms to keep track of attendance at all committee meetings and board meetings. | P | S | [19 empty] | x
Develop board calendar and start to list critical tasks that need to happen at each board meeting, | P | S | [19 empty] | x
Create mechanism (binder) for keeping track of all official policies. | P | S | [19 empty] | x
Create comprehensive list of all policies that need to be created before school opening. | S | P | [19 empty] | x
School Leader
Create a job description for the school leader |  |  | C |  | P | [16 empty] | X
Determine performance benchmarks/measures for school leader |  |  |  |  | P | [16 empty] | x
Create a clear process for evaluating the school leader |  |  |  |  | P | [16 empty] | x
Set a salary range based on industry standards |  |  |  |  | P | [16 empty] | x
Hire school leader |  |  | C |  | P | [16 empty] | x
Board Development
Create a board development plan to include orientation of new members, retreats, workshops, etc. | P | [20 empty] | x
Host Board Retreat | P | [20 empty] | x
Fund Development/ Fund Raising
Develop materials and messaging | S |  |  |  | P | [16 empty] | x
Identify potential individual donors | S |  |  |  | P
Solicit donations. | S |  |  |  | P
Secure public/private grant money
Identify sources | P S
Develop proposals/Apply | P | S
GALS Las Vegas Action Plan P= Primary; S= Secondary; C= Consultant Task/ Planning Area/ Timeline | ED | HOS | GALS | Staff | BOD | Volunteers | Prior | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Completed
Administrative
Data Management
Create filing system |  | S |  | P
Develop database for student reporting (e.g. bi-weekly progress reports |  | P |  | S
Develop student attendance reporting system |  | P |  | S
Procurement
Purchase supplies and materials for program | P
Secure janitorial services | P
Family Outreach
Write family letter re: Parent Orientation |  | P
Mail family letter re: Parent Orientation |  | P
Call all families re: Parent Orientation |  | P
Prepare pre-opening Parent Orientation protocol and materials |  | P
Hold pre-opening Parent Orientation |  | P
Curriculum, Teaching, and Learning
Curriculum Development
Identify preliminary models for core subjects |  | P |  | S | [17 empty] | x
Site visits to GALS schools |  | P |  | S | [18 empty] | on hold
Attend national and local educational conferences |  | P |  | S
Create and finalize curriculum plans and timelines |  | P |  | S
Create benchmarks aligned with state standards and curriculum frameworks |  | P |  | S
Create scope and sequence for each department |  | P |  | S
Procurement
Purchase materials and textbooks | S | P
Purchase standardized testing materials | S | P
Assessment
Define assessment strategy and timeline |  | P |  | S
Create baseline assessments and excel for data analysis |  | P |  | S
Conduct baseline testing of all students |  | P |  | S
Enter data from baseline tests |  | P |  | S
Instructional Program
Develop curriculum |  | P
--Scope and sequence for math and reading |  | P
GALS Las Vegas Action Plan P= Primary; S= Secondary; C= Consultant Task/ Planning Area/ Timeline | ED | HOS | GALS | Staff | BOD | Volunteers | Prior | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Completed
--Standards/mission for subjects |  | P
--Scope and sequence for all subjects |  | P | [19 empty] | x
--Preliminary in-house benchmarks - all subjects |  | P | [19 empty] | x
--Deadlines for in-house benchmark production |  | P
--Purchase materials, etc. |  | P
Create semester Tests - Math and Reading |  | P
Create semester Tests - Social Studies, Science, and Writing |  | P
Create student handbook, code of conduct |  | P
Finalize school calendar |  | P | [19 empty] | x
Develop class configuration - classroom model |  | P
Organize tutoring workshops and after school tutoring sched. |  | P | [19 empty] | N/A
Special Education
Recruit SPED/ELL coordinator/teacher/services |  | P |  | S | [17 empty] | x
Identify and secure specific texts and materials |  | P |  | S
Identify SPED student population |  | P |  | s
Acquire student records - sped records |  | P |  | S
Activate Student Success teams |  | P |  | S
Secure parent approval |  | P |  | S
Develop IEPs - if needed (update and review) |  | P |  | S
Define service requirements for all SPED students |  | P |  | S
School Culture and Climate
Finalize daily schedule |  | P |  | S | [17 empty] | x
Finalize school calendar | S | P | [19 empty] | x
Finalize discipline policy | S | P | [19 empty] | x
Develop special rituals/routines |  | P |  | S | [17 empty] | x
Establish PD pre-student enrollment | S | P
Financial Management
Develop preliminary Budget | P |  | S | [18 empty] | X
Finalize Budget | P |  | S | [18 empty] | x
Deliver Preliminary Budget to Board | P |  | S | [18 empty] | x
Codify the fiscal controls and financial policies the school will employ to track daily operational finances | P |  | S | [18 empty] | x
Identify check signers | P |  | S | [18 empty] | x
Identify check writers | P |  | S | [18 empty] | x
GALS Las Vegas Action Plan P= Primary; S= Secondary; C= Consultant Task/ Planning Area/ Timeline | ED | HOS | GALS | Staff | BOD | Volunteers | Prior | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Completed
Define signature policies | P |  | S | [18 empty] | x
Develop financial reporting templates (budget vs. actual) and policy | P |  | S | [18 empty] | x
Design process forms (purchase orders, expense forms) & policy | P |  | S | [18 empty] | x
Establish payroll | P |  | S | [18 empty] | x
Develop schedule of Board financial reviews | P |  | S | [18 empty] | x
implement school accounting system | P |  | S | [18 empty] | x
Set up a bank accounts | P |  | S | [18 empty] | X
Define investment/savings strategy (where will excess funds be placed) | P |  | S
Develop cash flow plan | P |  | S | [18 empty] | x
Personnel
Develop org chart and job descriptions | P | [20 empty] | x
Advertise/spread job descriptions | P | [20 empty] | x
Put together a literature packet on the school with information on: 1. Teaching calendar; 2. Professional development opportunities; 3. School mission |  | P | [19 empty] | x
Create job descriptions, flyers, and ads. | P | [20 empty] | x
Design the interview process (look at models) | P | [20 empty] | x
Design compensation and benefits packages | P | [20 empty] | x
Design a filing/documentation process. | P
Identify potential recruitment opportunities | P | [20 empty] | x
Advertise to web sources and job fairs | P | [20 empty] | x
Block out days for interviews on a calendar | P | [20 empty] | x
Design benefit packages, including retirement |  | P | [19 empty] | x
Recruit and hire Office Manager | P | [20 empty] | x
Recruit and hire teachers (place ads, etc.) | P | [20 empty] | x
Negotiate and sign agreements for contracted services | P | [20 empty] | x
Develop professional development plans |  | P | [19 empty] | x
Define policies and procedures for evaluation of staff | P
Develop staff handbook | P | [20 empty] | x
Perform background checks on employees | P | [20 empty] | x
Fill out forms to enroll teachers in 403(B) .Retirement | P
Have new staff fill out Employee Information forms (ie.emergency contact) |  |  |  | P
Plan and hold staff orientation /professional development |  | P
Transportation
GALS Las Vegas Action Plan P= Primary; S= Secondary; C= Consultant Task/ Planning Area/ Timeline | ED | HOS | GALS | Staff | BOD | Volunteers | Prior | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Completed
implement Biking program | P | S |  | S
Implementing Walking bus program |  | P
Food Service
Issue RFP | P | [20 empty] | x
Define requirement (# of students- any religious/indiv req) | P | [20 empty] | x
Identify free/reduced lunch students - contact DOE | P | [20 empty] | x
Determine food service arrangement | P | [20 empty] | x
Select vendor and draft contract | P
Sign contract | P
Develop food service policies - (menu, delivery time, logistics, etc.) | P | [20 empty] | x
Health and Safety
Complete all state reporting requirements
Identify doctor/nurse resources |  | P | [19 empty] | x
Identify first aid resources |  | P | [19 empty] | x
Develop a system for record-keeping |  |  | P
Develop policy for non-compliance by parents | P
Acquire medical forms - from parents (included in application) | P
Check for completeness | P
Report to the State of Nevada | P
Staff first aid training | P
Create and distribute health and safety handbook
Purchase first aid resources
Contact police and fire departments | P
Undergo fire inspection | P
Undergo building inspection | P
Contact Board of Health | P
Develop fire drill policy, schedule, route | P
Community Partnerships
Identify community partnership opportunities (continuous) | P | [20 empty] | x
Meet with potential partner organizations - access to fields | P | [20 empty] | X
Negotiate and sign agreement - (if applicable year one) | P
Devise performance measures for each strategic alliance | S
Parents and Community S
Parent/Student Handook(s)
GALS Las Vegas Action Plan P= Primary; S= Secondary; C= Consultant Task/ Planning Area/ Timeline | ED | HOS | GALS | Staff | BOD | Volunteers | Prior | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Completed
Get and study models of schools doing it well | P | [20 empty] | x
Draft content | P | [20 empty] | x
Edit handbook(s) | P | [20 empty] | x
Distribute final copies to parents/students. | P
Communication P
Design school logo | [21 empty] | x
Set up nonprofit mailing status with Post Office |  |  | P | [18 empty] | x
Develop filing system to store student academic, disciplinary & health records | P | [20 empty] | x
contacted about discipline infractions) | S |  |  | P
Define procedure for visitors entering building |  | P | [19 empty] | x
Develop forms necessary to track and monitor visitors ( | P | [20 empty] | x
Select provider for Internet access (DSL, cable) | P | [20 empty] | x
Set up Intranet (so all computers are linked) | P
Define how staff will communicate (email, walkie talkie, phones) | P | [20 empty] | x
Set up phone systems and answering services | P | [20 empty] | x
Purchasing P
Create a comprehensive list of all items that need to be purchased through Dec. of your 1st year (incase you have $ from your startup grant that will be lost if not spent right away)
Purchase classroom equipment and furniture | P
Purchase office equipment and furniture | P
Purchase postage meter | P
Purchase restroom supplies | P
Purchase cleaning products | P
Purchase library materials | P
Purchase science lab materials | P
Purchase art materials | P
Purchase movement equipment | P
Purchase medical supplies & furniture (ie. couch) | P
Purchase P.A. system | P
Purchase office supplies | P
Contract Personnel
SPED contractor |  | P
Professional Development personnel |  | P
GALS Las Vegas Action Plan P= Primary; S= Secondary; C= Consultant Task/ Planning Area/ Timeline | ED | HOS | GALS | Staff | BOD | Volunteers | Prior | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Completed
Line up pschylogist |  | P | [19 empty] | x
Technology
Write tech plan | P | [19 empty] | x
Computers for teachers | P
Cell phones for admin | P
Cell phones for teachers | P
Cojmputers for classroom. | P
Uniforms
Purchase GALS t-shirts | P | [20 empty] | x