## Summary
pilotED Schools of Nevada Inc - Operational and Planning Execution Plan
Assigned Pre-Opening Team Members: |  | Allen, Tejero, Luo, Morris, Mingo, Cook, Gonzalez
Area Addressed | Not Started | # in Progress | # Tasks Completed | Total Tasks | % Completed | Status
Governance & Management | 24 | 0 | 0 | 26 | 0% | Not Completed
Financial Management | 10 | 0 | 0 | 10 | 0% | Not Completed
Staffing | 9 | 0 | 0 | 9 | 0% | Not Completed
Curriculum & Instruction | 18 | 0 | 0 | 18 | 0% | Not Completed
Students & Families | 13 | 0 | 0 | 13 | 0% | Not Completed
Operations | 12 | 0 | 0 | 12 | 0% | Not Completed
Facilities, Furnishings, & Equipment | 11 | 0 | 0 | 11 | 0% | Not Completed
All Pre-Opening Tasks | 97 | 0 | 0 | 99 | 0% | Not Completed

## Governance
Number | Area Addressed | Area of Review | Documentation | Notes | Owner | Follow-up Actions | Month Prioritized | Completion Verified
GM.1 | Governance & Management | Permanent head(s) of school named and providing leadership for the school, and other key leadership roles in the school have been filled | Organizational Chart that delineates school-based and network-based personnel | School-created |  | Include in final application revision |  | No
GM.2 | Governance & Management | Permanent head(s) of school named and providing leadership for the school, and other key leadership roles in the school have been filled | Contract(s) and/or offer letters for school leader and key administrators | Specific document required (contracts) |  |  |  | No
GM.3 | Governance & Management | Board of Directors established and setting policy direction for the school | Copy of board meeting calendar for the upcoming school year | School-created |  |  |  | No
GM.4 | Governance & Management | Board of Directors established and setting policy direction for the school | Meeting minutes from at least one board meeting between February and July | School-created |  |  |  | No
GM.5 | Governance & Management | Board of Directors established and setting policy direction for the school | Current resumes for all board members | School-created |  | Included in application; may be updated |  | No
GM.6 | Governance & Management | Board of Directors established and setting policy direction for the school | Evidence that board training has occurred or is scheduled | School-created |  |  |  | No
GM.7 | Governance & Management | National criminal background checks completed for all current board members (IC 20-26-5-10) | Background check authorization and results are on file (Note: For the duration of the school's operation, the checks must also be completed 14 days prior to the approval of any new board members) | Specific document required (background checks) |  |  |  | No
GM.8 | Governance & Management | Determination of tax-exempt status from the IRS has been received (Charter Sec. 3.1) | Letter from IRS documenting tax-exempt status and number | Specific document required (IRS letter) |  | Filed by January |  | No
GM.9 | Governance & Management | Board of Directors established and setting policy direction for the school | Description of the board committee structure | School-created, this will be included in the final application |  |  |  | No
GM.10 | Governance & Management | Board of Directors established and setting policy direction for the school | Copy of current board bylaws and board policies | Specific document required (bylaws) |  | Include in final application revision |  | No
GM.11 | Governance & Management | Board of Directors established and setting policy direction for the school | Documentation of processes for conducting evaluations for school leader (including evaluation tool(s)) | Specific document required (evaluation tool) |  |  |  | No
GM.12 | Governance & Management | Board of Directors established and setting policy direction for the school | Documentation of processes for evaluation of CMO or EMO (including evaluation tool(s)) | Specific document required (evaluation tool) |  |  |  | No
GM.13 | Governance & Management | Board of Directors established and setting policy direction for the school | Documentation of processes for evaluation of the board (including evaluation tool(s)) | Specific document required (evaluation tool) |  |  |  | No
GM.14 | Governance & Management | CMO/EMO/ESP Contracts | Contracts with any CMO/EMO or ESP the school plans on utilizing | Specific document required (contracts) |  |  |  | No
GM.15 | Governance & Management | Data Sharing Agreement | MOU allowing the authorizer to access student-level data directly from the IDOE | Template |  |  |  | No
GM.16 | Governance & Management | Data Sharing Agreement | MOU allowing the authorizer to access student-level data directly from the NWEA (if applicable) | Template |  |  |  | No
GM.17 | Governance & Management | Board Communications | Authorizer meeting agenda and notes from at least one meeting with board chair prior to school opening | Agenda/Minutes | OEI |  | April | No
GM.18 | Governance & Management | Board Communications | Board meeting notes from authorizer pre-opening team's attendance of at least one meeting prior to school opening | Agenda/Minutes | OEI |  |  | No
GM.19 | Governance & Management | Charter Application | All sections of submitted full charter application updated and revised, if applicable. | Template |  |  | July (prior to walk through) | No
GM.20 | Governance & Management | Board of Directors established and setting policy direction for the school | Board roster using the Template | Template |  | Included in application; may be updated |  | No
GM.21 | Governance & Management | Board of Directors established and setting policy direction for the school | Signed assurance forms | Template |  |  |  | No
GM.22 | Governance & Management | Board of Directors established and setting policy direction for the school | Evidence of annual board/school goals (formal tracking system) | School-created |  |  |  | No
GM.23 | Governance & Management | Board of Directors established and setting policy direction for the school | Incident Communication Assurance Form | Template |  |  |  | No
GM.24 | Governance & Management | Board of Directors established and setting policy direction for the school | Articles of Incorporation | Specific document required from Nevada SOS |  |  |  | No
Note on D10: CAVAZOS, SHAINA R.: Do we need this separate from what's included in the final application?
Note on E16: CAVAZOS, SHAINA R.: For templates in general, let's decide if they all live online or in a shared folder, for ease of access

## Finance
Number | Area Addressed | Area of Review | Documentation | Notes | Owner | Follow-up Actions | Month Prioritized | Completion Verified
FM.1 | Financial Management | School has adopted proper internal financial and accounting controls | School must retain an independent certified public accountant or firm licensed in IN to perform an agreed-upon procedure engagement (the "Independent Accountants Report") in accordance with standards established by the American Institute of Certified Public Accountants. Report must include findings from reviewing Procedures 1-6 detailed below. | Engagement letter specifying completion by first day of school |  |  |  | No
FM.2 | Financial Management | School has adopted proper internal financial and accounting controls | Procedure #1: Obtain a copy of the accounting procedures manual of the school and read it to ascertain whether it includes accounting procedures for the preparation of the school's financial statement in conformity with generally accepted accounting principles for not-for-profit organizations | Specific document required (audit), full audit will be completed in August of next year |  |  |  | No
FM.3 | Financial Management | School has adopted proper internal financial and accounting controls | Procedure #2: Read the accounting manual to ascertain whether it includes payroll procedures for the school and whether the school will hire an outside vendor to process the payroll | Specific document required (audit) |  |  |  | No
FM.4 | Financial Management | School has adopted proper internal financial and accounting controls | Procedure #3: Read the accounting manual to ascertain whether it includes procedures for accounting for contributions and grants | Specific document required (audit) |  |  |  | No
FM.5 | Financial Management | School has adopted proper internal financial and accounting controls | Procedure #4: Read the available trial balance and documentation supporting cash receipts, cash distributions, and payroll expenses to observe the status of implementation of the accounting procedures (for organizations with current cash flow only - such as replications or network expansions). | Specific document required (audit) |  |  |  | No
FM.6 | Financial Management | School has adopted proper internal financial and accounting controls | Procedure #5: Identify and interview the person(s) responsible for the financial management of the school regarding the existence of procedures for the creation and review by management of quarterly financial reports | Specific document required (audit) |  |  |  | No
FM.7 | Financial Management | School has adopted proper internal financial and accounting controls | Procedure #6: Interview the person(s) responsible for financial management of the school regarding existence of appropriate internal financial controls and procedures, including procedures related to ensuring that transactions are properly authorized, assets are safeguarded against unauthorized or improper use, and transactions are properly recorded and reported | Specific document required (audit) |  |  |  | No
FM.8 | Financial Management | School has adopted proper internal financial and accounting controls | Board-approved, written description of the school's financial management policies, including the board's process for approving expenditures, plan for preparing financial statements in accordance with generally accepted accounting principles and requirements as set forth by IN's State Board of Accounts (SBOA), payroll procedures, accounting for contributions and grants, procedures for the creation and review of quarterly financial statements, which shall specifically identify the individual who will be responsible for preparing such financial statements, and appropriate internal financial controls and procedures | Specific document required (audit) |  |  |  | No
FM.9 | Financial Management | Financial Plan | 1- year cash flow plan identifying the sources of funds available to pay start-up costs and costs of operations prior to receipt of state and local tuition support | template |  | Include in final application revision |  | No
FM.10 | Financial Management | Financial Plan | 5-year detailed budget that also identifies start-up costs | template |  | Include in final application revision |  | No
Note on D3: CAVAZOS, SHAINA R.: Some folks were confused for these items about who is responsible. For instance, who reads the accounting manual? OEI or school?
Note on E3: CAVAZOS, SHAINA R.: I'm assuming "audit" here refers to the procedure engagement, rather than an annual audit? If so, would it be clearer to change the term from "audit" to "report" or something like that?

## Staffing
Number | Area Addressed | Area of Review | Documentation | Notes | Owner | Follow-up Actions | Month Prioritized | Completion Verified
S.1 | Staffing | Number of teachers is adequate and assignments match the staffing plan | Written staffing plan outlining number of staff at each grade level and all administrative positions | School-created |  | Include in final application revision |  | No
S.2 | Staffing | Documentation of clear lines of authority and responsibility | Position descriptions | School-created |  | Include in final application revision |  | No
S.3 | Staffing | Develop substitue teacher pool or plan for class coverage | Signed contract and/or written documentation of plan | School-created |  |  |  | No
S.4 | Staffing | Create employee handbook | Copy of handbook should include evidence of evaluation policy, dress code, school specific personnel policies and procedures | School-created |  |  |  | No
S.5 | Staffing | Retirement Benefits are in place for appropriate staff | Evidence that arrangements have been made for contributing to public retirement funds | School-created |  |  |  | No
S.6 | Staffing | All staff positions have been filled and employment applications and contracts are on file for each staff member | Completed employee spreadsheet including names, position title, license numbers, and sign off on background checks. Monitor via pre-opening agenda to track progress towards 100% staffed | template |  |  |  | No
S.7 | Staffing | Special Education Teaching Staff (Teacher of Record) | Signed contracts for special education teachers and/or service providers if needed |  |  |  |  | No
S.8 | Staffing | Special Education Teaching Staff (Teacher of Record) | Evidence that special education teachers hold valid certifications in the state of NV. If special education teacher holds limited license or emergency permit, submit a plan for license completion |  |  |  |  | No
S.9 | Staffing | National Criminal background checks for all staff and volunteers have been completed | School policy and procedure for obtaining and filing National Criminal background checks for all staff members and volunteers who have regular contact with children (including parent and volunteers) | School-created |  |  |  | No

## Curriculum
6 | Area Addressed | Area of Review | Documentation | Notes | Owner | Follow-up Actions | Month Prioritized | Completion Verified
CI.1 | Curriculum & Instruction | Curriculum | Detailed, specific summary of curriculum (only if modifications have been made from initial charter application). Should include a curriculum map aligned to NV standards. Submission can include a pacing guide. | School-created |  | Include in final application revision |  | No
CI.2 | Curriculum & Instruction | Instructional materials and supplies | Evidence that materials and supplies are in order and will be delivered in time for school opening | School-created |  |  |  | No
CI.3 | Curriculum & Instruction | School calendar (Charter Section 17.7) | Comprehensive calendar that includes, for example, first and last days of school, days school closed for vacation or staff development, school make-up days due to bad weather, community meetings, field trips, parent nights. | School-created |  |  |  | No
CI.4 | Curriculum & Instruction | School calendar (Charter Section 17.7) | Assessment calendar that includes all state mandated assessments as well as school-based diagnostic, formative, and summative assessment dates, as well as description for common planning/data analysis times for staff | School-created |  |  |  | No
CI.5 | Curriculum & Instruction | School-specififc Goals | School has finalized school-specific academic and non-academic goals for years 1-7. | OEI template |  | Include in final application revision |  | No
CI.6 | Curriculum & Instruction | Class schedules | Schedule of classes for each grade and/or subject area. Note total instructional minutes by subject and common planning time | School-created |  |  |  | No
CI.7 | Curriculum & Instruction | Summer PD | Submit plan for PD session content, modules and materials. Ensure IEP training in teacher induction training |  |  |  |  | No
CI.8 | Curriculum & Instruction | Comprehensive Special Education Plan | Comprehensive plan for how the school will deliver services to students with special needs. The plan must comply with all applicable state and federal laws and include items #1-13 below | School-created |  |  |  | No
CI.9 | Curriculum & Instruction | Comprehensive Special Education Plan | #3 Evidence that supports are in place for all school staff and personnel to assist students with IEPs | School-created |  |  |  | No
CI.10 | Curriculum & Instruction | Comprehensive Special Education Plan | #4 Sample of blank legal documentations to be utilized by the school for all special education procedures and processes | School-created |  |  |  | No
CI.11 | Curriculum & Instruction | Comprehensive Special Education Plan | #6 Proposed plan for ensuring adequate special education staffing, plans for testing accommodations including and beyond SBAC, NWEA, WIDA, or any other school wide assessment | School-created |  |  |  | No
CI.12 | Curriculum & Instruction | Comprehensive Special Education Plan | #7 Proposed school wide behavior support plan to be implemented | School-created |  |  |  | No
CI.13 | Curriculum & Instruction | Comprehensive Special Education Plan | #8 Accountability and liability measures in place with outside contractors providing special education services | School-created |  |  |  | No
CI.14 | Curriculum & Instruction | Comprehensive Special Education Plan | #9 Specifically address how procedures for due process and mediation hearings will be handled | School-created |  |  |  | No
CI.15 | Curriculum & Instruction | Comprehensive Special Education Plan | #10 Plan for aggregating data for exceptional needs across disability labels | School-created |  |  |  | No
CI.16 | Curriculum & Instruction | Comprehensive Special Education Plan | #13 Copy of the student handbook briefly describing the philosophy, supports, and procedures for special education services | School-created |  |  |  | No
CI.17 | Curriculum & Instruction | Instructional materials and supplies | Evidence that materials and supplies are in stock in time for school opening (occurs during final walk-through) | No document |  |  | July (during final walkthrough) | No
CI.18 | Curriculum & Instruction | Socio-emotional support services | Evidence that staff are on board to provide socio-emotional services as needed, and/or evidence that arrangements have been made for contracted services | School-created |  |  |  | No

## StudentsandFamilies
Number | Area Addressed | Area of Review | Documentation | Notes | Owner | Follow-up Actions | Month Prioritized | Completion Verified
SF.1 | Students & Families | Documentation of recruiting and admission process for the upcoming school year (Charter Section 17.7) 2 months before enrollment lottery | Evidence of lottery process | School-created |  |  |  | No
SF.3 | Students & Families | Documentation of recruiting and admission process for the upcoming school year (Charter Section 17.7) 2 months before enrollment lottery | Evidence of submission of Match Targets in alignment with Charter Projected Enrollment | School-created |  | Include in final application revision |  | No
SF.4 | Students & Families | Documentation of recruiting and admission process for the upcoming school year (Charter Section 17.7) 2 months before enrollment lottery | Active website that includes enrollment information and FAQs | School-created |  |  |  | No
SF.5 | Students & Families | School enrollment is on track to meet the Charter Projected Enrollment submitted in the Charter Application | Round 1 of enrollment results show a significant number of matches that puts the school on its way to meet enrollment targets | Specific document required (Enroll Indy report) |  |  |  | No
SF.6 | Students & Families | Orientation scheduled and held for students and families | Marketing materials; sign-in from orientation session; yearly and weekly calendar and handbooks shared w/parents; confirm distribution of textbook assistance/medical ahd health forms | School-created |  | calendar, student and family handbook must be finalized in advance of orientation |  | No
SF.7 | Students & Families | Student policies (including suspension and expulsion) have been established and are available to students and parents in written form | Copy of student handbook which includes suspension and expulsion policies, student graduation and promotion policies, and a school-wide culture/behavior plan | School-created |  | Include in final application revision |  | No
SF.8 | Students & Families | Student policies (including suspension and expulsion) have been established and are available to students and parents in written form | Copy of procedure/policy for families to contact the school and/or board with complaints or concerns (may be included in the student handbook) | School-created |  | Include in final application revision |  | No
SF.9 | Students & Families | Student policies (including suspension and expulsion) have been established and are available to students and parents in written form | Identify and interview person responsible for school culture to gather evidence of transition routines, other behaviors | School-created |  |  |  | No
SF.9 | Students & Families | Procedures are in place for collecting students' prior school cumulative records and for securely storing student academic, attendance, special education, and discipline records | Evidence that procedures are in place for efficiently collecting students' records from sending schools, including asking former school for any possible special education records for all enrolled students- school must demonstrate it is taking responsibility for ensuring special education records are obtained in a timely fashion (e.g. records request form signed by parents will be sent to both the school and the district office specifically requesting both cumulative and special education records; the records will be requested far in advance of the start of school; and the school has additional follow-up steps in place to ensure all records are received in a timely manner) | School-created |  |  |  | No
SF.10 | Students & Families | Procedures are in place for collecting students' prior school cumulative records and for securely storing student academic, attendance, special education, and discipline records | Evidence that procedures are in place for securely storing student academic, attendance, and discipline records, including but not limited to special education files and data | School-created |  |  |  | No
SF.11 | Students & Families | Process in place for students to get uniforms | Evidence should include contract w/school uniform vendor; written documentation to parents regarding uniform procurement process | School-created |  |  |  | No
SF.12 | Students & Families | Electronic system for maintaining student records has been implemented (Charter Section 6.5) | Evidence that an electronic system is in place (information should be easily aggregated and disaggregated by race, gender, school corporation of residence, special education, free/reduced lunch, date of enrollment, date of withdrawal, previous schooling, etc) | Specific document required (contract or order summary) |  |  |  | No
SF.13 | Students & Families | Projected student enrollment (Charter Section 17.7) | Department of Education Membership Estimate Count for New Schools | Specific document required (DOE report) |  |  | May; with updated enrollment numbers at every meeting. | No
Note on D7: CAVAZOS, SHAINA R.: They explain these in the app, but not as a full handbook. I think this should be submitted as a separate document like the employee handbook.
Note on D9: CAVAZOS, SHAINA R.: Confusion around this last year. Who does this? Is this still necessary?

## Operations
Number | Area Addressed | Area of Review | Documentation | Notes | Owner | Follow-up Actions | Month Prioritized | Completion Verified
O.1 | Operations | Arrangements have been made for food services | Food or vendor services contract | Specific document required (contract) |  |  |  | No
O.2 | Operations | Arrangements have been made for food services | Evidence a Clark County Health Department inspection has been scheduled and an application has been submitted to the Clark County Health Department | School-created |  |  | Scheduled by April | No
O.3 | Operations | Arrangements have been made for food services | Licensed to serve food from Clark County Health Department | Specific document required (license) |  |  |  | No
O.4 | Operations | School safety and emergency preparedness | Specific, detailed plan for preparing for/responding to emergencies that complies with applicable laws. Evacuation plan includes procedures for students with exceptional needs that ensure safety and dignity (resources at: | School-created |  |  |  | No
O.5 | Operations | School safety and emergency preparedness | Determine placement (inside and outside) policies and procedurus for all secuirty guards to ensure alignment with school culture and rules | School-created |  |  |  | No
O.6 | Operations | School safety and emergency preparedness | Establish entering and exiting systems for students and determine which external doors will be open during the day | School-created |  |  |  | No
O.7 | Operations | School safety and emergency preparedness | Determine traffic pattern for dropping off and picking up students | School-created |  |  |  | No
O.8 | Operations | Provisions have been made for health services, screening, and immunization records | Evidence that health services are available (school nurse on staff or contract, contract with local health facility, etc) | Specific document required (contract) |  |  |  | No
O.9 | Operations | Provisions have been made for health services, screening, and immunization records | Written description that procedures are in place for administering student medication (e.g. specific staff members identified and trained to administer medication) | School-created |  |  |  | No
O.10 | Operations | Transportation | Final, detailed plan including copies of contracts | Specific document required (contract) |  |  |  | No
O.11 | Operations | Transportation | Evidence of plan for providing transportation specific to students with exceptional needs if required by IEP | School-created (unless delineated in contract) |  |  |  | No
0.12 | Operations | Lead Testing agreement and schedule | Documentation of communication with Marion County Health Department for students in grades 1 and below to receive lead testing | MCO Health Dept. Documentation |  |  |  | No
Note on E3: CAVAZOS, SHAINA R.: Do we need some direction here for innovation schools about what the innovatio agreement will or won't cover?

## Facilities
Number | Area Addressed | Area of Review | Documentation | Notes | Owner | Follow-up Actions | Month Prioritized | Completion Verified
FFE.1 | Facilities, Furnishings & Equipment | Insurance coverage for Commercial General Liability and Umbrella Liability | Certificates of insurance for Commercial General liability and Umbrella liability (Coverages take effect no later than effective date of acquisition of physical plan and comply with terms of the charter) | Specific document required (insurance certificates) |  | Include in final application revision |  | No
FFE.2 | Facilities, Furnishings & Equipment | Organizer has acquired, through purchase, lease or otherwise, the location and facility for the school | Purchase or lease agreement | Specific document required (lease) |  |  |  | No
FFE.3 | Facilities, Furnishings & Equipment | The creation of a timeline for renovating or completing the facility | Copy of comprehensive plan outlining proposed dates for completion of construction or renovation of facility | School-created |  |  |  | No
FFE.4 | Facilities, Furnishings & Equipment | The necessary steps are being taken to ensure all inspections are competed in a timely manner prior to opening | Evidence inspections have been scheduled with Clark County Health Department, State Fire Marshall/North Las Vegas Fire Department, and City Building Inspector | School-created |  |  |  | No
FFE.5 | Facilities, Furnishings & Equipment | The necessary steps are being taken to ensure all inspections are competed in a timely manner prior to opening | Evidence that all inspections are to be completed no later than two weeks prior to school opening | School-created |  |  |  | No
FFE.6 | Facilities, Furnishings & Equipment | All required zoning permits have been obtained | Permits and certifications for ZONING from the City of North Las Vegas Department of Metropolitan Development and Department of Public Works deeming facility suitable for a school | Specific document required (permits) |  |  |  | No
FFE.7 | Facilities, Furnishings & Equipment | All required land use permits have been obtained | Permits and certification for LAND USE from the City of North Las Vegas Department of Metropolitan Development and Department of Public Works deeming facility suitable for a school | Specific document required (permits) |  |  |  | No
FFE.8 | Facilities, Furnishings & Equipment | All required building related permits have been obtained | Permits and certifications related to BUILDING USE from the City of North Las Vegas Department of Metropolitan Development and Department of Public Works deeming facility suitable for a school | Specific document required (permits) |  |  |  | No
FFE.9 | Facilities, Furnishing & Equipment | The necessary steps have been taken to ensure all inspections are completed in order for the school to open and that all buildings are universally accessible for students, families, and visitors with exceptional needs | Copies of the final inspection reports | Specific document required (inspection reports) |  |  |  | No
FFE.10 | Facilities, Furnishing & Equipment | The necessary steps have been taken to ensure all inspections are completed in order for the school to open and that all buildings are universally accessible for students, families, and visitors with exceptional needs | Architect's Project Completion Certification disclosing the official date of completion for the construction and/or renovation of the facility. The letter should also include whether variance requests were made with Board of Zoning Appeals and the date of the hearing | Specific document required (Letter) |  |  |  | No
FFE.11 | Facilities, Furnishing & Equipment | Mayor's office approval of physical plan will occur after a final walk through of the facility | Letter of approval is granted upon completion of of the pre-opening process | No document |  |  | July (during walkthrough) | No
Note on E3: CAVAZOS, SHAINA R.: Can we be specific about where the innovation agreement would cover things here?