## Ongoing Monthly Tasks
Task Name | Description and Evidence | Resources/External Contacts | SPCSA Team | Deadline
Incubation Year Board Meeting Agendas, Minutes, and Draft Minutes | As board meetings occur, the agendas are submitted to Epicenter and properly posted on the school's website and notice.nv.gov. Draft and approved meeting minutes for all board meetings are submitted to Epicenter and posted on the school's website. | https://notice.nv.gov/ | Authorizing | Ongoing--Monthly
Identification of Governing Board Contacts in Epicenter | Update Epicenter with all governing board member information, including term lengths. Board center should be updated as necessary, and the roster in Epicenter should match the roster on the school's website. | For information on how to add and maintain governing board contacts in Epicenter, please refer to this Epicenter Resource: https://support.epicenternow.org/home/board-member-management/adding-and-updating-board-members/ | Authorizing | Ongoing--Monthly
Identification of School Contacts in Epicenter | Update Epicenter with all required school contacts as they are hired and identified: - School Leader - Financial Officer - Grant Contact - McKinney Vento Contact - SPED Contact - Foster Contact - EL Contact - Assessment and Accountability Contact - Title I Contact - Emergency Contact | For information on how to add and maintain school contacts in Epicenter, please refer to this Epicenter Resource: https://support.epicenternow.org/home/updating-contacts/updating-contacts-in-school-and-management-center/ | Authorizing | Ongoing--Monthly
Monthly Enrollment Report | Complete the survey monthly to provide data regarding student enrollment. Survey link: https://forms.office.com/g/j82bFUEyzN | The link to the survey will be provided in the monthly Epicenter task. | Authorizing | Ongoing--Monthly
SPCSA Check-Ins | Starting in December 2024, school leaders and representatives from the board meet with SPCSA staff monthly regarding the progress of pre-opening tasks throughout the incubation year. |  | All | Ongoing--Monthly
SPCSA Training | School leaders and/or governing board members must participate in all training required by the SPCSA for new schools. | A training schedule will be provided by December 2024. | All | Ongoing--Monthly

## Pre-Opening Tasks
Category | Task Name | Description and Evidence | Resources/External Contacts | SPCSA Team | Deadline
Planning and Preparation | Incubation Year Plan | Updated version of incubation year plan which includes all items in the pre-opening checklist |  | Authorizing | 2025-01-15
Board Governance | Board Meeting Calendar | Board meetings for the upcoming school year are scheduled, and schedule is posted on the school's website. Submit a screenshot or URL of the school's website that shows the board meeting calendar for the upcoming school year. |  | Authorizing | 2025-01-15
Board Governance | Board Roster | Board roster is posted on the school's website and includes board contact information (i.e. email address). Submit a screenshot or URL of the school's website that shows an accurate board roster with contact information. |  | Authorizing | 2025-01-15
Board Governance | Board Member Disclosure Forms and Resumes | All board members have completed disclosure forms and submitted a resume or professional bio and copy of teacher license, if applicable. |  | Authorizing | 2025-01-15
Board Governance | Board Policy and Procedures Manual, Code of Ethics, and Bylaws | The charter school board has adopted the following key items: a -Policy and Procedures Manual, Code of Ethics, and Bylaws. |  | Authorizing | 2025-01-15
Board Governance | Board Policy - Criminal Background Check | The charter school board has adopted a criminal background check policy for board members, staff, and volunteers in alignment with NRS 388A.323 and NRS 386.588. |  | Authorizing | 2025-01-15
Board Governance | Non-profit Incorporation | The charter school has a certificate of incorporation or similar documentation, if applicable. Additionally, the charter school has filed for a tax-exempt letter and federal identification number from the IRS. Submit documentation for BOTH the certification of incorporation and the tax-exempt letter/federal identification number from the IRS. | https://www.nvsos.gov/sos/businesses | Authorizing | 2025-01-15
Board Governance | Management Contract with CMO or EMO, if applicable | If the schools was approved to contract with a CMO or EMO, the school's board has approved and signed a management contract with the CMO or EMO (as applicable). |  | Authorizing | 2025-03-15
Enrollment, Students, and Families | Student Lottery Policy, Application, and Lottery Dates | The charter school has a board approved lottery policy, calendar, and proposed application to be used for students to submit names to the lottery for the upcoming school year. The application is compliant with NRS 388A.453, NRS 388A.456, and R131-16. Additionally, include the lottery opening date, lottery closing date, and the date the lottery will be held. These key dates will be posted to the SPCSA website and should be easily accessible on individual school websites as well. |  | Authorizing | 2025-02-15
Enrollment, Students, and Families | EL Policies and Handbook | The charter school board has approved policies and procedures describing how the school will provide services to English Learners in compliance with state and federal laws and regulations. | SPCSA Model Handbook | School Support | 2025-02-15
Enrollment, Students, and Families | Notification to Households within a 2-mile radius | The charter school has complied with NRS 388A.450 and provided notification to households within 2 miles of the school. Provide a copy of the mailer and a receipt for sending. | NRS 388A.450 | Authorizing | 2025-02-15
Enrollment, Students, and Families | Parent and Student Handbook | NAC 388A and NRS 392 require that schools adopt written rules in compliance with certain policies and protocls in the form of a Parent and Student Handbook, which must be annually approved, reviewed, and/or amended by the charter school's governing board. The handbook must be distributed at the start of each school year and posted on the school's website. It should include, but is not limited to, the following: - Operational protocols - Volunteering procedures, included required background checks, training, and check-in practices. -Student drop off/pick up procedures with times and locations - Rights of students with diverse learning needs - Available courses - Code of Honor - Policies on enrollment, attendance, retention/promotion/graduation - Behavioral rules and consequences - Restorative Discipline policy, including students with disabilities - Appeal of suspension/expulsion - Complaint policy, including how to file a formal complaint - No fee or required donation for student to attend charter school - FERPA policy - FOIL/Public Records policy - Health policies, including those for administering medicine - School calendar and schedule - Rights of individuals to attend Board meetings |  | Authorizing (School Support to Review Restorative Justice/Discipline Plan) | 2025-03-15
Enrollment, Students, and Families | Special Education Policies and Procedures Manual | The charter school board has approved policies and procedures describing how the school will provide special education services in compliance with IDEA and applicable Nevada laws and regulations. Submit these approved policies and sign and submit the Special Education Attestation included in the Epicenter task. | SPCSA Model Handbook | School Support | 2025-03-15
Enrollment, Students, and Families | McKinney-Vento Policy | The charter school board has approved policies and procedures describing how the school identifies and provides supports for students eligible under the McKinney-Vento Homeless Assistance Act (per Title IX, Part A of the Elementary and Secondary Education Act, as amended by the Every Student Succeeds Act). For high schools, policies must address partial credit and the awarding of high school diplomas pursuant to NRS 389.320-389.330. | SPCSA Model Handbook | School Support | 2025-03-15
Enrollment, Students, and Families | Foster Care Policy | The charter school board has approved policies and procedures describing how the school identifies and provides supports for students in foster care. For high schools, policies must address partial credit and the awarding of high school diplomas pursuant to NRS 389.320-389.330. | SPCSA Model Handbook | School Support | 2025-03-15
Enrollment, Students, and Families | School Calendar | The charter school board has approved a school calendar. Submit the draft calendar to Epicenter and the NDE portal: https://app.smartsheet.com/b/publish?EQBCT=e12981f9a7f64b9db12acec3e8c9b4f4. | The application and forms are provided on NDE's portal. | Authorizing | 2025-05-01
Enrollment, Students, and Families | Gender Identity Policy and Training | In accordance with NAC 388.880, the governing board of each charter school is required to adopt a policy that contains requirements and methods for addressing certain rights and needs of persons with diverse gender identities or expressions. Additionally, the regulation requirest that each school employee receives annual training concerning the requirements and needs of persons with diverse gender identities or expressions. Please submit your policy and evidence of a plan to provide the training for the 2025-2026 school year. | NRS 388.133 and NAC 388.880 | Authorizing | 2025-05-15
Enrollment, Students, and Families | Enrollment Audit | Each new charter school will have an enrollment conducted in June. Submit all required paperwork and rosters by June 1. *The default first PCFP payment is August 1, however, in accordance with NRS 387.1241, a charter school may request the first payment to occur on July 1 and the Superintendent of Public Instruction may approve such a request. If requesting an early payment, the school enrollment audit is also conducted 1 month earlier and the deadline will be 5/1/2025. |  | School Support | 2025-06-01
Management: Administration, Staff, Personnel | Staff Evaluation Measures and Process | Provide a copy of the performance evaluation criteria, designed evaluation, and outlined process, with timetable, for: - School leader - Teachers - Other school administrators and non-instructional staff |  | Authorizing | 2025-01-15
Management: Administration, Staff, Personnel | Staff Handbook | The charter school's board has approved an Employee Handbook. Provide a copy of the handbook and evidence of a plan to distribute it to all employees. |  | Authorizing | 2025-03-15
Management: Administration, Staff, Personnel | Registration with Department of Public Safety | The charter school is required to create an account with the Department of Public Safety to conduct background checks. Provide evidence this account has been created and is active. |  | Authorizing | 2025-04-15
Management: Administration, Staff, Personnel | Staffing Directory | Provide a copy of the staff directory, in accordance with the staffing plan in the charter application. For teachers, include grade, subjects taught, and the expiration date of their teaching license. Include non-instructional staff and contract employees (i.e., special education consultants, cafeteria workers, security) used by the school. For administrators, teachers, and other licensed staff, include the license number to demonstrate compliance with NRS 388A.518. | NRS 388A.518 | Authorizing | 2025-07-15
Management: Administration, Staff, Personnel | Completed background checks | Certify that the charter school has completed and plans to continue to complete background checks for each employee and any identified student-facing volunteers. |  | Authorizing | 2025-07-15
Management: Administration, Staff, Personnel | Employee Contracts/Job Agreements | Provide an employee contract template or sample of a signed employee contract with position description and employment terms. |  | Authorizing | 2025-07-15
Management: Administration, Staff, Personnel | Staff Professional Development and Orientation | Provide written evidence that orientation has taken place for staff to familiarize them with mission and program of school and to clarify their roles and responsibilities (i.e., agendas, sign-in sheets, etc.). If the orientation is upcoming, provide a schedule and communication to staff regarding the orientation. |  | School Support | 2025-07-15
Financial Management | PERS | Provide confirmation from Public Employee Retirement System (PERS) that the school is set up appropriately for the first year of operation. | https://www.nvpers.org/front | Authorizing | 2025-02-15
Financial Management | Fiscal Policies and Procedures | The charter school must have fiscal policies and procedures that are compliant with Uniform Guidance 2 C.F.R. Part 200. 1) Submit a copy of the charter school's written Fiscal Policies and Procedures Manual that includes each of the required seven fiscal topics (Internal Controls, Allowability of Costs, Accounting and Financial Management Systems, Procurement Systems, Audit Resolution, Inventory Management, and Records Retention). 2) Complete and submit the Fiscal Policies and Procedures Checklist (see attached resource document). Please read the additional instructions and guidance included in the checklist. *During the self-assessment, if it is discovered that one or more required criteria is omitted, please make the necessary corrections prior to submitting. |  | Finance and Operations | 2025-02-15
Financial Management | Grant Management System | Complete the application linked below for access to the SPCSA’s Grant Management System (GMS). Certify that the school has completed the GMS application. https://forms.monday.com/forms/00a1ad40444f377ed114efa1618298d7?r=use1 |  | Finance and Operations | 2025-03-15
Financial Management | Nevada Bank Account | The charter school must establish a bank account in Nevada to receive state and federal funds. Provide a letter or document demonstrating that the schools has established such an account. |  | Authorizing | 2025-03-15
Financial Management | Budget--Tentative | The charter school's board is required to review the school's tentative budget for 2025 -- 2026 fiscal year and host a budget hearing for public input. Provide the following documents: 1. Tentative Budget for the fiscal year with detailed assumptions for all key revenues and expenditures, including reasonable enrollment. 2. Evidence the Budget has been made available to the public. 3. Evidence of the Scheduled Budget Hearing during the 2nd or 3rd week in May (can be in conjunction with a board meeting). | NAC 387.720 | Authorizing | 2025-04-15
Financial Management | Federal Grant Registration | The charter school must register for Unique Entity Identifier (UEI). Provide written evidence of the UEI. | https://sam.gov/content/entity-registration | Finance and Operations | 2025-04-15
Financial Management | Accounting System and Chart of Accounts | The charter school and board must be prepared to conduct extensive accounting and financial reporting. Include the following items: 1. Identify the accounting system the charter school plans to use, including internal controls and fiscal policies. 2. Provide evidence of or attestation that school will use the state chart of accounts and has the appropriate accounting systems in place to do so. 3. Provide documentation of employment of or contract with an accountant, bookkeeper, or other person or entity to handle fiscal duties at the school. | NAC 387.785 | Authorizing | 2025-04-15
Financial Management | New and Expanding School Grant Information | Provide enrollment projections, including special populations, and complete any required paperwork to qualify for new/expanding school provision under federal grants. Use the form attached to the Epicenter task regarding the enrollment projections. |  | Finance and Operations | 2025-05-15
Financial Management | Budget--Final | The charter school's board must approve a final budget for the 2025--2026 fiscal year with detailed assumptions for all key revenues and expenditures. The Final Budget should include revenue based upon the school's confirmed enrollment and expenses that incorporate the cost of the identified facility. | NAC 387.725 | Authorizing | 2025-06-08
Financial Management | Nevada State Vendor Registration | The charter school must obtain registration for Nevada state vendor number. Provide evidence of registration, including either the paper or online form submitted to the Controller's Office. | Register as a vendor with the Nevada State Controller’s Office https://controller.nv.gov/Buttons/ElectronicVendorReg/ | Finance and Operations | 2025-06-15
Financial Management | Five-year Budget | The charter school's governing board should develop and approve a five-year budget aligned to provisions of approved charter application and submit to Epicenter. |  | Authorizing | 2025-06-15
Financial Management | Detailed monthly cash-flow projection for first-year of operations | The charter school's board should develop monthly cash flow projections for the first year of operations and submit to Epicenter. |  | Authorizing | 2025-06-15
Operations | Health Services | Develop a written plan for the provision of required health services (i.e., hearing and vision screenings). The plan should include internal practices and procedures for monitoring student health needs and administering prescription and non-prescription medication, including auto-injectable epinephrine pursuant to NRS 388A.547. |  | School Support | 2025-04-15
Operations | Notification to local police and fire departments | The charter school should notify the local police and fire department of their existence and open a dialogue regarding public safety. Provide evidence that the local police and fire department have been notified and any action items required by public safety officers have been shared with the SPCSA. Provide evidence of communication of the following information: - Location of the school; - Floor plan of the school; - Names of authorized contact persons for the charter school, including, without limitations, the principal and vice principal of the school; - The number of pupils enrolled in the charter school; - The maximum number of pupils that may enroll in the charter school. | NRS 388A.363 | Authorizing | 2025-05-15
Operations | Food Services Contract | If the charter school plans to provide food services, provide a copy of the following items: -The food/vendor services contract -Registration with the Nevada Department of Agriculture as a School Food Agency |  | School Support | 2025-06-15
Operations | Transportation | ONLY FOR SCHOOLS OFFERING TRANSPORTATION: 1. Copy of contract with bus company. 2. Transportation plan, including copy of health and safety certificates and copies of background check for transportation provider 3. Proof of appropriate and required insurance that meets local and statutory requirements 4. Evidence of approvals for NDE and Nevada Department of Transportation 5. Transportation Driver Certification 6. Confirmation of Vehicle Inspection. | NDE Website: https://doe.nv.gov/Pupil_Transportation/Home/ | Authorizing | 2025-06-15
Operations | Annual School Committee Emergency Operations Plan Review for Crisis/Emergency | The charter school must annually provide evidence of the School Committee's annual review of the Emergency Operations Plan. Provide evidence of a list of participants that comply with NRS 388.247 and evidence the meeting was held (for example, a sign in sheet). Additionally, complete the Notice of Completion and post to the school's website. Submit a screenshot or URL that demonstrates the Notice has been posted. | NRS 388.247-388.249 | School Support | 2025-06-15
Operations | Emergency Operations Plan | The charter school and board must develop an Emergency Operations Plan and submit to the Nevada Division of Emergency Management. Information regarding the development of the Emergency Operations Plan can be found on NDE's website: https://doe.nv.gov/emergency-management/home/. 1. Submit the Emergency Operations Plan to the Nevada Division of Emergency Management's Emergency Response Plan Portal, using Access Code R219953: https://app.smartsheet.com/b/form/07f3ad5a1fd54397bced6cb95b66e761. 2. Submit the confirmation of your plan submission to DEM as well as copies of each EOP. |  | School Support | 2025-06-30
Operations | Student Records | The charter school must have policies and procedures regarding student record-keeping. Submit a copy of these policies and procedures. |  | School Support | 2025-07-15
Operations | School Nurse | Provide written evidence the school has made arrangements to be staffed with a school nurse and has procedures for administering medicine. |  | School Support | 2025-07-15
Academic Program, Instruction, and Curriculum | Data and Reporting Systems | The charter school must utilize Infinite Campus as the Student Information System. Provide a signed contract with Infinite Campus, the implementation/training plan, and the members of the school's staff that will participate in the training/implementation. |  | Authorizing | 2025-02-15
Academic Program, Instruction, and Curriculum | Assessment Materials and Systems | The charter school is required to provide certain assessments to students. Provide evidence that the following assessment materials have been purchased, if applicable: - Brigance (if using for the Kindergarten Entry Assessment) - NWEA MAP (if using for more than K-3 Reading) |  | Authorizing | 2025-02-15
Academic Program, Instruction, and Curriculum | Annual Testing Calendar Submission | The SPCSA annually collects testing calendars. Develop an assessment calendar that provides specific testing dates (not the general NDE windows) for the following assessments, at minimum: -Smarter Balanced (SBAC) (Grades 3-8), including dates for math and ELA -Science (grades 5 and 8) -High School Science (grade 9 or 10) -ACT (grade 11) -Kindergarten Entry Assessment, including test being used (MAP or Brigance) -NWEA MAP Reading (grades K-3), including dates for fall, winter, and spring administrations -Nevada Alternate Assessment (grades 3-8 and 11), including dates for math, ELA, and science -WIDA ACCESS for ELLs (grades K-12) -WIDA screener (grades K-12) -Career and Tehcnical Education (CTE Program Completers) -Civics Test (Before graduation) |  | Authorizing | 2025-05-15
Academic Program, Instruction, and Curriculum | Learning Management System | Evidence that the following learning management system setup has been completed: - Canvas Schools need to be sure that user accounts for students have been created in Infinite Campus for Canvas Implementation to function. The SPCSA will setup the API. Note that schools are not required to use student accounts. | Setup Student Accounts in Infinite Campus (you don't need to actually give students the accounts - they just need to exist) instructions are found here: https://kb.infinitecampus.com/help/user-account-batch-wizard#UserAccountBatchWizard-CreatingStudentAccounts | School Support | 2025-07-15
Facilities | Entitlements | Submit copies of zoning permits and land use approval. |  | Authorizing | 2025-02-15
Facilities | Traffic Study | Submit a copy of the Traffic study approval. |  | Authorizing | 2025-03-15
Facilities | Building Permits and Construction Schedule | Submit required building permits for any construction and/or renovation. Additionally, provide a construction schedule demonstrating that the school will have a TCO or COO in place 30 days before the first day of school. |  | Authorizing | 2025-03-15
Facilities | School Location | Provide evidence that the location of the school is identified and publicly known (i.e., on school website). Submit a screenshot or URL of the school's website that identifies the location of the school. |  | Authorizing | 2025-06-15
Facilities | Facility Lease -- Approved | Submit a copy of the approved lease and/or purchase documents with all applicable party signatures. The lease/purchase document should include the physical address of the facility. The facility should meet the needs of the school and be located in one of the following zip codes: 89030, 89031, 89032, or 89081. |  | Authorizing | 2025-06-01
Facilities | Confirmation of Insurance Coverage | A charter school shall obtain insurance from an authorized insurer and submit the certificate, listing the SPCSA as additional insured. Pursuant to NAC 388A.190, Industrial insurance coverage is to be in accordance with the applicable provisions of the Nevada Industrial Insurance Act, chapters 616A and 616D, inclusive. | NAC 388A.190-388A.195 | Authorizing | 2025-06-15
Facilities | Certificate of Occupancy | Submit a copy of the Certificate of Occupancy or Temporary Certificate of Occupancy demonstrating compliance with NRS 388A.360, which requires a school facility to be has been inspected and meets the requirements of any applicable building codes, codes for the prevention of fire, and codes pertaining to safety, health and sanitation. | NRS 388A.360 | Authorizing | 30 days before first day of school
Facilities | Adequate and accessible space | Submit a copy of the written procedures for accommodation of handicapped persons in compliance with ADA |  | Authorizing | 2025-07-15
Facilities | Health Permit (School & Kitchen) | If the charter school plans to provide food services, provide a copy of the Health permit for the school and kitchen. |  | Authorizing | 2025-07-15

## Walkthrough Checklist
Category | Task Name | Description and Evidence | SPCSA Team | Deadline
Walkthrough | Instructional Materials & Supplies | Instructional materials and supplies are visible and evident | Authorizing | At Walkthrough
Walkthrough | Accessibility | Clear procedure for entrance and egress from the building that ensures student safety | Authorizing | At Walkthrough
Walkthrough | Fire Extinguishers | Fire extinguishers on all floors have been inspected and tagged. | Authorizing | At Walkthrough
Walkthrough | Elevators | Current Elevator permits are posted | Authorizing | At Walkthrough
Walkthrough | Mandated Reporting | Mandated Reporting policies and evidence of training conducted (ex. sign-in sheet) | Authorizing | At Walkthrough
Walkthrough | Hazardous Areas | All electrical rooms, mechanical rooms, breaker or fuse boxes, janitorial closets with cleaners/chemicals, and other hazardous areas off limit to students are locked except when accessed by authorized personnel | Authorizing | At Walkthrough
Walkthrough | Informational/Directional Signage | Exterior signage identifying the school name and address and interior signage for rooms, bathrooms, and directions. | Authorizing | At Walkthrough
Walkthrough | Safety Signage | Exit and fire/evacuation signage posted; classrooms have posted evacuation plans. | Authorizing | At Walkthrough
Walkthrough | Symbols/Signs | Space is free from all religious symbols, signs, or representations. | Authorizing | At Walkthrough
Walkthrough | Postings and Policies | Required state and federal employment laws are posted in an area that staff can readily access/review them. | Authorizing | At Walkthrough
Walkthrough | Securing Student Records | All student records (academic, IEP, health, etc.) are stored in lockable storage containers or password protected electronic storage system. | Authorizing | At Walkthrough
Walkthrough | Nurse's office | 1. Adequate Space for Treatment and Storage of Medical Records. 2. Locking medical cabinet and lockable refrigerator. 3. Sharps container for the disposal of sharps, including needles, syringes, etc. | School Support | At Walkthrough
Walkthrough | Working Internet Access | School has working internet access, as verified by SPCSA staff during walkthrough | Authorizing | At Walkthrough
Walkthrough | Assessment Administration Readiness | Evidence that school have been added to relevant assessment systems and applicable school staff have accounts for training and administration purposes. | Authorizing | At Walkthrough