## Ongoing Monthly Tasks
Task Name | Description and Evidence | Resources/External Contacts | SPCSA Team | Deadline
Incubation Year Board Meeting Agendas, Minutes, and Draft Minutes | As board meetings occur, the agendas are submitted to Epicenter and properly posted on the school's website and notice.nv.gov. Approved meeting minutes for all board meetings are submitted to Epicenter and posted on the school's website. | https://notice.nv.gov/ | Authorizing | Ongoing--Monthly
Identification of Governing Board Contacts in Epicenter | Update Epicenter with all governing board member information, including term lengths. Board center should be updated as necessary, and the roster in Epicenter should match the roster on the school's website. | For information on how to add and maintain governing board contacts in Epicenter, please refer to this Epicenter Resource: https://support.epicenternow.org/home/board-member-management/adding-and-updating-board-members/ | Authorizing | Ongoing--Monthly
Identification of School Contacts in Epicenter | Update Epicenter with all required school contacts as they are hired and identified: - School Leader - Financial Officer - Grant Contact - McKinney Vento Contact - SPED Contact - Foster Contact - EL Contact - Assessment and Accountability Contact - Title I Contact - Emergency Contact -Charter School Attorney (if applicable) | For information on how to add and maintain school contacts in Epicenter, please refer to this Epicenter Resource: https://support.epicenternow.org/home/updating-contacts/updating-contacts-in-school-and-management-center/ | Authorizing | Ongoing--Monthly
Monthly Enrollment Report | Complete the survey monthly to provide data regarding student enrollment. Survey link: https://forms.cloud.microsoft/g/BLNbHvYL8S | The link to the survey will be provided in the monthly Epicenter task. | Authorizing | Ongoing--Monthly
SPCSA Check-Ins | Starting in December 2026, school leaders and representatives from the board meet with SPCSA staff monthly regarding the progress of pre-opening tasks throughout the incubation year. |  | All | Ongoing--Monthly
SPCSA Training | School leaders and/or governing board members must participate in all training required by the SPCSA for new schools. | A training schedule will be provided by December 2026. | All | Ongoing--Monthly

## Pre-Opening Tasks
Category | Task Name | Description and Evidence | Resources/External Contacts | SPCSA Team | Deadline
Planning and Preparation | Incubation Year Plan | Updated version of incubation year plan which includes all items in the pre-opening checklist. |  | Authorizing | 2027-01-15
Board Governance | Board Meeting Calendar | Board meetings for the upcoming school year are scheduled, and schedule is posted on the school's website. Submit a screenshot or URL of the school's website that shows the board meeting calendar for the upcoming school year. |  | Authorizing | 2027-01-15
Board Governance | Board Roster | Board roster is posted on the school's website and includes board contact information (i.e. email address). Submit a screenshot or URL of the school's website that shows an accurate board roster with contact information. |  | Authorizing | 2027-01-15
Board Governance | Board Member Disclosure Forms and Resumes | All board members have completed disclosure forms and submitted a resume or professional bio and copy of teacher license, if applicable. |  | Authorizing | 2027-05-15
Board Governance | Board Policy and Procedures Manual, Code of Ethics, and Bylaws | The charter school board has adopted a Policy and Procedures Manual, Code of Ethics, and Bylaws. |  | Authorizing | 2027-01-15
Board Governance | Board Policy - Criminal Background Check | The charter school board has adopted a criminal background check policy for board members, staff, and volunteers in alignment with NRS 388A.323 and NRS 386.588. |  | Authorizing | 2027-02-15
Board Governance | Non-profit Incorporation | The charter school has a certificate of incorporation or similar documentation, if applicable. Additionally, the charter school has filed for a tax-exempt letter and federal identification number from the IRS. Submit documentation for BOTH the certification of incorporation and the tax-exempt letter/federal identification number from the IRS. | https://www.nvsos.gov/sos/businesses | Authorizing | 2027-01-15
Board Governance | Management Contract with CMO or EMO, if applicable | If the schools was approved to contract with a CMO or EMO, the school's board has approved and signed a management contract with the CMO or EMO (as applicable). |  | Authorizing | 2027-03-15
Enrollment, Students, and Families | Student Lottery Policy, Application, and Lottery Dates | The charter school has a board approved lottery policy, calendar, and proposed application to be used for students to submit names to the lottery for the upcoming school year. The application is compliant with NRS 388A.453, NRS 388A.456, and R131-16. Additionally, include the lottery opening date, lottery closing date, and the date the lottery will be held. These key dates will be posted to the SPCSA website and should be easily accessible on individual school websites as well. |  | Authorizing | 2027-01-15
Enrollment, Students, and Families | EL Policies and Handbook | The charter school board has approved policies and procedures describing how the school will provide services to English Learners in compliance with state and federal laws and regulations. | SPCSA Model Handbook | School Support | 2027-02-15
Enrollment, Students, and Families | Notification to Households within a 2-mile radius | The charter school has complied with NRS 388A.450 and provided notification to households within 2 miles of the school. Provide a copy of the notification and documentation demonstrating that the required notification was distributed (e.g., a copy of the mailer, email or other electronic notification, mailing receipt, distribution record, or other documentation verifying notification). | NRS 388A.450 | Authorizing | 2027-02-15
Enrollment, Students, and Families | Parent and Student Handbook | NAC 388A and NRS 392 require that schools adopt written rules in compliance with certain policies and protocols in the form of a Parent and Student Handbook, which must be annually reviewed and/or amended, then approved by the school's governing board. The handbook must be distributed to families at the start of each school year and posted on the school's website. To complete this taks, submit a copy of the handbook AND a completed checklist. | Changes to Appeal Process Guidance and a Parent and Student Handbook Checklist are included in the Epicenter task as resources. | Authorizing (School Support to Review Restorative Justice/Discipline Plan) | 2027-03-15
Enrollment, Students, and Families | Special Education Policies and Procedures Manual | The charter school board has approved policies and procedures describing how the school will provide special education services in compliance with IDEA and applicable Nevada laws and regulations. Submit these approved policies and sign and submit the Special Education Attestation included in the Epicenter task. | SPCSA Model Handbook | School Support | 2027-03-15
Enrollment, Students, and Families | McKinney-Vento Policy | The charter school board has approved policies and procedures describing how the school identifies and provides supports for students eligible under the McKinney-Vento Homeless Assistance Act (per Title IX, Part A of the Elementary and Secondary Education Act, as amended by the Every Student Succeeds Act). For high schools, policies must address partial credit and the awarding of high school diplomas pursuant to NRS 389.320-389.330. | SPCSA Model Handbook | School Support | 2027-03-15
Enrollment, Students, and Families | Foster Care Policy | The charter school board has approved policies and procedures describing how the school identifies and provides supports for students in foster care. For high schools, policies must address partial credit and the awarding of high school diplomas pursuant to NRS 389.320-389.330. | SPCSA Model Handbook | School Support | 2027-03-15
Enrollment, Students, and Families | School Calendar | The charter school board has approved a school calendar. Submit the draft calendar to Epicenter and the NDE portal: https://app.smartsheet.com/b/publish?EQBCT=e12981f9a7f64b9db12acec3e8c9b4f4. | The application and forms are provided on NDE's portal. | Authorizing | 2027-05-01
Enrollment, Students, and Families | Gender Identity Policy and Training | In accordance with NAC 388.880, the governing board of each charter school is required to adopt a policy that contains requirements and methods for addressing certain rights and needs of persons with diverse gender identities or expressions. Additionally, the regulation requirest that each school employee receives annual training concerning the requirements and needs of persons with diverse gender identities or expressions. Please submit your policy and evidence of a plan to provide the training for the 2027-2028 school year. | NRS 388.133 and NAC 388.880 | Authorizing | 2027-05-15
Management: Administration, Staff, Personnel | Staff Evaluation Measures and Process | Provide a copy of the performance evaluation criteria, designed evaluation, and outlined process, with timetable, for: - School leader - Teachers - Other school administrators and non-instructional staff |  | Authorizing | 2027-03-15
Management: Administration, Staff, Personnel | Staff Handbook | The charter school's board has approved an Employee Handbook. Provide a copy of the handbook and evidence of a plan to distribute it to all employees. |  | Authorizing | 2027-03-15
Management: Administration, Staff, Personnel | Registration with Department of Public Safety | The charter school is required to create an account with the Department of Public Safety to conduct background checks. Provide evidence that the required documentation has been completed and submitted to the appropriate entities. |  | Authorizing | 2026-12-15
Management: Administration, Staff, Personnel | All Staff Report | Provide a copy of the staff report, in accordance with the staffing plan in the charter application. On the Detail tab, complete data cells for all persons who are or will be employed/contracted in the current school year at the time of completing this report. Submitted reports must reflect the nearest FTE for each person for the current school year based on drop-down options. All applicable cells must have data entered. Please refer to the directions in each column in the template. Note: This report will be updated and submitted again in October. | All Staff Report | Authorizing | 2027-07-15
Management: Administration, Staff, Personnel | Completed background checks | Certify that the charter school has completed and plans to continue to complete background checks for each employee and any identified student-facing volunteers. |  | Authorizing | 2027-07-15
Management: Administration, Staff, Personnel | Employee Contracts/Job Agreements | Provide an employee contract template or sample of a signed employee contract with position description and employment terms. |  | Authorizing | 2027-07-15
Management: Administration, Staff, Personnel | Staff Professional Development and Orientation | Provide the plan for staff orientation to familiarize them with mission and program of school and to clarify their roles and responsibilities. Provide a schedule and communication to staff regarding the orientation. |  | School Support | 2027-07-15
Financial Management | PERS | Provide confirmation from Public Employee Retirement System (PERS) that the school is set up appropriately for the first year of operation. | https://www.nvpers.org/front | Authorizing | 2027-02-15
Financial Management | Fiscal Policies and Procedures | The charter school must have fiscal policies and procedures that are compliant with Uniform Guidance 2 C.F.R. Part 200. 1) Submit a copy of the charter school's written Fiscal Policies and Procedures Manual that includes each of the required seven fiscal topics (Internal Controls, Allowability of Costs, Accounting and Financial Management Systems, Procurement Systems, Audit Resolution, Inventory Management, and Records Retention). 2) Complete and submit the Fiscal Policies and Procedures Checklist (see attached resource document). Please read the additional instructions and guidance included in the checklist. *During the self-assessment, if it is discovered that one or more required criteria is omitted, please make the necessary corrections prior to submitting. |  | Finance and Operations | 2027-02-15
Financial Management | Grant Management System | Complete the application linked below for access to the SPCSA’s Grant Management System (GMS). Certify that the school has completed the GMS application. | https://forms.office.com/g/hm8PiRABYC | Finance and Operations | 2027-03-15
Financial Management | Nevada Bank Account | The charter school must establish a bank account in Nevada (NRS 388a.411) to receive state and federal funds. Provide a letter or document demonstrating that the schools has established such an account. |  | Authorizing | 2027-03-15
Financial Management | Budget--Tentative | The charter school's board is required to review the school's tentative budget for 2027 -- 2028 fiscal year and host a budget hearing for public input. Provide the following documents: 1. Tentative Budget for the fiscal year with detailed assumptions for all key revenues and expenditures, including reasonable enrollment. 2. Evidence the Budget has been made available to the public. 3. Evidence of the Scheduled Budget Hearing during the 2nd or 3rd week in May (can be in conjunction with a board meeting). | NAC 387.720 | Authorizing | 2027-04-15
Financial Management | Federal Grant Registration | The charter school must register for Unique Entity Identifier (UEI). Provide written evidence of the UEI. | https://sam.gov/content/entity-registration | Finance and Operations | 2027-02-15
Financial Management | Accounting System and Chart of Accounts | The charter school and board must be prepared to conduct extensive accounting and financial reporting. Include the following items: 1. Identify the accounting system the charter school plans to use, including internal controls and fiscal policies. 2. Provide evidence of or attestation that school will use the state chart of accounts and has the appropriate accounting systems in place to do so. 3. Provide documentation of employment of or contract with an accountant, bookkeeper, or other person or entity to handle fiscal duties at the school. | NAC 387.785 | Authorizing | 2027-04-15
Financial Management | New and Expanding School Grant Information | Provide enrollment projections, including special populations, and complete any required paperwork to qualify for new/expanding school provision under federal grants. Use the form attached to the Epicenter task regarding the enrollment projections. |  | Finance and Operations | 2027-02-15
Financial Management | Budget--Final | The charter school's board must approve a final budget for the 2027--2028 fiscal year with detailed assumptions for all key revenues and expenditures. The Final Budget should include revenue based on the fully enrolled student count at the time of board approval and accurately incorporate expenses for the identified facility. | NAC 387.725 | Authorizing | 2027-06-08
Financial Management | Nevada State Vendor Registration | The charter school must obtain registration for Nevada state vendor number. Provide evidence of registration, including either the paper or online form submitted to the Controller's Office. | Register as a vendor with the Nevada State Controller’s Office https://controller.nv.gov/Buttons/ElectronicVendorReg/ | Finance and Operations | 2027-02-15
Financial Management | Five-year Budget | The charter school's governing board should develop and approve a five-year budget aligned to provisions of approved charter application and submit to Epicenter. Enrollment in Year 1 of the projections should align with enrollment established during the enrollment audit and within the school's final budget. |  | Authorizing | 2027-06-15
Financial Management | Detailed monthly cash-flow projection for first-year of operations | The charter school's board should develop monthly cash flow projections for the first year of operations and submit to Epicenter. These projections should align with enrollment established during the enrollment audit and within the school's final budget. |  | Authorizing | 2027-06-15
Operations | Health Services | Develop a written plan for the provision of required health services (i.e., hearing and vision screenings). The plan should include internal practices and procedures for monitoring student health needs and administering prescription and non-prescription medication, including auto-injectable epinephrine pursuant to NRS 388A.547. |  | School Support | 2027-04-15
Operations | Notification to local police and fire departments | The charter school should notify the local police and fire department of their existence and open a dialogue regarding public safety. Provide evidence that the local police and fire department have been notified and any action items required by public safety officers have been shared with the SPCSA. Provide evidence of communication of the following information: - Location of the school; - Floor plan of the school; - Names of authorized contact persons for the charter school, including, without limitations, the principal and vice principal of the school; - The number of pupils enrolled in the charter school; - The maximum number of pupils that may enroll in the charter school. | NRS 388A.363 | Authorizing | 2027-05-15
Operations | Notice to Department of Agriculture | If the charter school plans to provide food services, email Erica Jaramillo (ejaramillo@agri.nv.gov) at the Department of Agriculture and include the name of the school, contact information, projected Y1 enrollment, and that the school is a new charter school interested in offering food services. Submit a screenshot of the email. |  | School Support | 2027-02-15
Operations | Food Services Contract | If the charter school plans to provide food services, provide a copy of the following items: -The food/vendor services contract -Registration with the Nevada Department of Agriculture as a School Food Agency |  | School Support | 2027-06-15
Operations | Annual School Committee Emergency Operations Plan Review for Crisis/Emergency | The charter school must annually provide evidence of the School Committee's annual review of the Emergency Operations Plan. Provide evidence of a list of participants that comply with NRS 388.247 and evidence the meeting was held (for example, a sign in sheet). Additionally, complete the Notice of Completion and post to the school's website. Submit a screenshot or URL that demonstrates the Notice has been posted. | NRS 388.247-388.249 | School Support | 2027-07-30
Operations | Emergency Operations Plan | The charter school and board must develop an Emergency Operations Plan and submit to the Nevada Division of Emergency Management. Information regarding the development of the Emergency Operations Plan can be found on NDE's website: https://doe.nv.gov/emergency-management/home/. 1. Submit the Emergency Operations Plan to the Nevada Division of Emergency Management's Emergency Response Plan Portal, using Access Code R219953: https://app.smartsheet.com/b/form/07f3ad5a1fd54397bced6cb95b66e761. 2. Submit the confirmation of your plan submission to DEM as well as copies of each EOP. |  | School Support | 2027-07-12
Operations | Student Records | The charter school must have policies and procedures regarding student record-keeping. Submit a copy of these policies and procedures. |  | School Support | 2027-07-15
Operations | School Nurse | Provide written evidence the school has made arrangements to be staffed with a school nurse and has procedures for administering medicine. |  | School Support | 2027-07-15
Academic Program, Instruction, and Curriculum | Data and Reporting Systems | The charter school must utilize Infinite Campus as the Student Information System. Provide a signed contract with Infinite Campus, the implementation/training plan, and the members of the school's staff that will participate in the training/implementation. |  | Authorizing | 2027-02-15
Academic Program, Instruction, and Curriculum | School Performance Plan | School should submit a board approved School Performance Plan for the 2026-27 school year in Plan4Learning. Certify via Epicenter that the plan has been submitted. |  | School Support | 2027-05-15
Academic Program, Instruction, and Curriculum | High School Programs | For all relevant high school programs, submit the following: --Provide evidence of partnership with colleges or universitites to offer dual credit programs in compliance with NRS 389.310. This is required of all schools approved to offer grades 9-12. --If the school intends to offer Career and Technical Education courses during the 2027-28 school year, provide evidence that any Career and Technical Education courses comply with NDE requirements and that those courses for which students will earn academic credit have been approved by the State Board of Education in alignment with NAC 389.672. --If the school intends to offer work-based learning during the 2027-28 school year, provide evidence that the school has received approval from the State Board of Education in accordance with NRS 389.167. |  | School Support | 2027-07-15
Academic Program, Instruction, and Curriculum | Annual Testing Calendar Submission | The SPCSA annually collects testing calendars. Develop an assessment calendar that provides specific testing dates (not the general NDE windows) for the following assessments, at minimum: -Smarter Balanced (SBAC) (Grades 3-8), including dates for math and ELA -Science (grades 5 and 8) -High School Science (grade 9 or 10) -ACT (grade 11) -Kindergarten Entry Assessment -Read by Grade 3 Assessment (NWEA MAP or iReady) for grades K-3, including dates for fall, winter, and spring administrations -Nevada Alternate Assessment (grades 3-8 and 11), including dates for math, ELA, and science -WIDA ACCESS for ELLs (grades K-12) -WIDA screener (grades K-12) -Career and Tehcnical Education (CTE Program Completers) -Civics Test (Before graduation) Note: The school's proposed assessment calendar may need to change upon the release of the 2027-28 calendar from NDE. Updated calendars will be collected in the fall. | https://webapp-strapi-paas-prod-nde-001.azurewebsites.net/uploads/calendar_be727bc5ff.pdf | Authorizing | 2027-05-15
Facilities | Entitlements | Submit copies of zoning permits and land use approval. |  | Authorizing | 2027-03-15
Facilities | Traffic Study | Submit a copy of the Traffic study approval. |  | Authorizing | 2027-03-15
Facilities | Building Permits and Construction Schedule | Submit required building permits for any construction and/or renovation. Additionally, provide a construction schedule demonstrating that the school will have a TCO or COO in place 30 days before the first day of school. |  | Authorizing | 2027-03-15
Facilities | School Location | Provide evidence that the location of the school is identified and publicly known (i.e., on school website). Submit a screenshot or URL of the school's website that identifies the location of the school. |  | Authorizing | 2027-06-15
Facilities | Facility Lease -- Approved | Submit a fully executed lease for a facility that will meet the needs of the school for the 2027-28 school year within the approved zip codes. The lease/purchase document should include the physical address of the facility. |  | Authorizing | 2027-06-01
Facilities | Confirmation of Insurance Coverage | A charter school shall obtain insurance from an authorized insurer and submit the certificate, listing the SPCSA as additional insured. Pursuant to NAC 388A.190, industrial insurance coverage is to be in accordance with the applicable provisions of the Nevada Industrial Insurance Act, chapters 616A to 616D, inclusive of NRS. A charter school shall obtain insruance from an authorized insurer and submit the certificate(s) including an Endorsement--Broad Form Policy, listing the SPCSA as named insured as well as NAC 388A.190.1(b)2-4. All required coverages listed in NAC 388A.190 must be present on the submitted certificate(s). If Workers Compensation is through a different provider, submit that certificate as well. If any coverages are NOT noted on the certificate but indicated within the policy, please submit both and indicate the page number where coverage(s) can be found. Common Abbreviations of Coverage Types as noted in NAC 388A.190: 1(b)(4): for directors and Executive Directors: D&O 1(d): Educators' Legal Liability: ELL 1(e): Employment Practices Liability: EPLI 1(f): Employment Benefits Liability: EBL 1(g): Covering Errors and Omissions of the Sponsor and Governing Body of the Charter School: E&O |  | Authorizing | 2027-06-15
Facilities | Certificate of Occupancy | Submit a copy of the Certificate of Occupancy or Temporary Certificate of Occupancy demonstrating compliance with NRS 388A.360, which requires a school facility to be has been inspected and meets the requirements of any applicable building codes, codes for the prevention of fire, and codes pertaining to safety, health and sanitation. | NRS 388A.360 | Authorizing | 30 days before first day of school
Facilities | Adequate and accessible space | Submit a copy of the written procedures for accommodation of handicapped persons in compliance with ADA. |  | Authorizing | 2027-07-15
Facilities | Health Permit (School & Kitchen) | If the charter school plans to provide food services, provide a copy of the Health permit for the school and kitchen. |  | Authorizing | 2027-07-15
Unique Conditions: Legal Prep | CMO Contract | By January 1, 2027, provide evidence that the board has approved a Charter Management Organization (CMO) contract that outlines the specific roles and responsibilities of all parties during the incubation year and the first year of operation. This contract must be in compliance with all relevant Nevada laws and regulations. |  | Authorizing | 2027-01-01
Unique Conditions: Pahrump Valley | High Quality Classical Education Partner | Provide evidence that the school has secured a formal partnership with a high-quality classical education partner capable of supporting the faithful implementation of a strong classical education. |  | Authorizing | 2026-11-01
Unique Conditions: Pahrump Valley | Budget | Submit a revised incubation year budget that clearly reflects all anticipated expenses and is balanced and supported by documentation of any grant, fundraising, or private revenue. Additionally, submit a detailed 3-year financial forecast for the first three years of the charter contract (FY2027, FY2028, and FY2029) that includes enrollment projections, revenue, expenses, and ending fund balances. |  | Authorizing | 2026-11-01
Unique Conditions: Pahrump Valley | Professional Development Plan | Submit a revised professional development plan that includes staff training in the classical education model delivered by the selected classical education partner. |  | Authorizing | 2027-03-15
Unique Conditions: Somerset Academy Carson City | School Leader | Provide evidence that a school leader has been hired. |  | Authorizing | 2027-01-01
Unique Conditions: Northern Nevada Wildflower | School Leader | Provide evidence that a school leader has been hired. |  | Authorizing | 2027-01-01

## Walkthrough Checklist
Category | Task Name | Description and Evidence | SPCSA Team | Deadline
Walkthrough | Instructional Materials & Supplies | Instructional materials and supplies are visible and evident | Monitoring & Evaluation | At Walkthrough
Walkthrough | Accessibility | Clear procedure for entrance and egress from the building that ensures student safety | Monitoring & Evaluation | At Walkthrough
Walkthrough | Fire Extinguishers | Fire extinguishers on all floors have been inspected and tagged. | Monitoring & Evaluation | At Walkthrough
Walkthrough | Elevators | Current Elevator permits are posted | Monitoring & Evaluation | At Walkthrough
Walkthrough | Mandated Reporting | Mandated Reporting policies and evidence of training conducted (ex. sign-in sheet) | Monitoring & Evaluation | At Walkthrough
Walkthrough | Hazardous Areas | All electrical rooms, mechanical rooms, breaker or fuse boxes, janitorial closets with cleaners/chemicals, and other hazardous areas off limit to students are locked except when accessed by authorized personnel | Monitoring & Evaluation | At Walkthrough
Walkthrough | Informational/Directional Signage | Exterior signage identifying the school name and address and interior signage for rooms, bathrooms, and directions. | Monitoring & Evaluation | At Walkthrough
Walkthrough | Safety Signage | Exit and fire/evacuation signage posted; classrooms have posted evacuation plans. | Monitoring & Evaluation | At Walkthrough
Walkthrough | Symbols/Signs | Space is free from all religious symbols, signs, or representations. | Monitoring & Evaluation | At Walkthrough
Walkthrough | Postings and Policies | Required state and federal employment laws are posted in an area that staff can readily access/review them. | Monitoring & Evaluation | At Walkthrough
Walkthrough | Securing Student Records | All student records (academic, IEP, health, etc.) are stored in lockable storage containers or password protected electronic storage system. | Monitoring & Evaluation | At Walkthrough
Walkthrough | Nurse's office | 1. Adequate Space for Treatment and Storage of Medical Records. 2. Locking medical cabinet and lockable refrigerator. 3. Sharps container for the disposal of sharps, including needles, syringes, etc. | Monitoring & Evaluation | At Walkthrough
Walkthrough | Working Internet Access | School has working internet access, as verified by SPCSA staff during walkthrough | Monitoring & Evaluation | At Walkthrough
Walkthrough | Assessment Administration Readiness | Evidence that school have been added to relevant assessment systems and applicable school staff have accounts for training and administration purposes. | Monitoring & Evaluation | At Walkthrough